## topkpi_report_20210723074426
Bergrivier Municipality
Section 52 Quarter 4 2020/21
Office of the Municipal Manager
Strategic Objective | KPI Name | Description of Unit of Measurement | Base-line | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Sustainable Service Delivery | The percentage of the municipal capital budget actually spent on capital projects as at 30 June 2021 (Actual amount spent on capital projects/ Total amount budgeted for capital projects) X 100 | % of Capital budget spent as at 30 June 2021 [(Actual amount spent on capital projects/Total amount budgeted for capital projects) X100] | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 85.99% | O | [D702] Municipal Manager: By far the biggest capital budget is allocated to the Technical Directorate and the reasons for underspending will be included in his performance evaluation. One serious contributing factor remains the Covid-19 pandemic and the first and second waves experienced during this financial year. A spending of 85.99% is commended under the current circumstances. (June 2021) | 95% | 95% | 85.99% | O
Strengthen Financial Sustainability and further enhance Good Governance | 100% compliance with Selection & Recruitment Policy when vacant posts within the 3 highest levels of management are filled subject to suitably qualified candidates | % compliance with the selection and recruitment policy | 1% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G | [D703] Municipal Manager: None required (June 2021) | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Improve staff productivity & responsiveness through quarterly leadership development meetings and/or initiatives | Number of Leadership Forum Meetings and/or other leadership initiatives | 4 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 4 | B | [D704] Municipal Manager: None required (June 2021) | 1 | 1 | 4 | B
Strengthen Financial Sustainability and further enhance Good Governance | Effectively manage and ensure compliance on a quarterly basis of all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | % of quarterly compliance with all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Stand-Alone | 95% | 0% | 95% |  | 75% | O | [D705] Municipal Manager: The finance department was requested to correctly allocate the capital budget to the directorate responsible for the execution of the ward project and not budget it under the co-ordinator of the wards. Council is further requested not to approve unspendable amounts in the adjustment budget. (June 2021) | 95% | 95% | 75% | O
Strengthen Financial Sustainability and further enhance Good Governance | Evaluate the performance of all staff with performance contracts (T12 - T18) on an annual basis according to the agreed upon performance contracts before 30 June 2021 | % of performance evaluations of all staff with performance contracts (T12 - T18) according to the agreed upon performance contracts before 30 June 2021 | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Last Value | 100% | 0% | 100% |  | 100% | G | [D706] Municipal Manager: None required (June 2021) | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Update the Eunomia system on a monthly basis to ensure that there is adherence to the regulatory and statutory requirements of all relevant legislation and regulations and submit to EMC on a monthly basis | Number of Eunomia reports submitted to EMC to ensure the adherence to the regulatory and statutory requirements of all relevant legislation and regulations | 12 | 11 | 11 | Whole of Municipality: All | Number | Accumulative | 3 | 0 | 3 |  | 3 | G | [D707] Municipal Manager: None required (June 2021) | 3 | 3 | 3 | G
Strengthen Financial Sustainability and further enhance Good Governance | MFMA Section 131(1): Ensure that any issues raised by the Auditor General in an Audit Report are addressed by 30 June 2021 | % of issues raised by the Auditor General in an audit report addressed by 30 June 2021 | 1% | 100% | 100% | Whole of Municipality: All | Percentage | Carry Over | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop a risk based audit plan with an internal audit plan (RBAP) (MFMA - Section 165(2)(a)) & submit to Audit Committee by 30 June 2021 | RBAP with internal audit programme submitted to the Audit Committee by 30 June 2021 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Convene a Councillor & Senior Management strategic planning session for IDP & budget process by 30 October 2020 | Strategic planning session held by 30 October 2020 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Communicate with the public on a regular basis through printed and social media in the official languages of the Western Cape | Number of editions and/ or communications | 16 | 20 | 20 | Whole of Municipality: All | Number | Accumulative | 5 | 0 | 5 |  | 10 | B | [D711] Head: Communication: None required. (June 2021) | 5 | 5 | 10 | B
Strengthen Financial Sustainability and further enhance Good Governance | Regular ward committee meetings and/or engagements before 30 June 2021 (depending on Covid-19 regulations) | Number of ward committee meetings and/or engagements before 30 June 2021 | 42 | 21 | 14 | Whole of Municipality: All | Number | Accumulative | 14 | 0 | 14 |  | 0 | R | [D712] Head Strategic Services: No Individual ward meeting took place due to the Covid-19 regulations (April 2021) [D712] Head Strategic Services: Scheduled ward meetings was cancelled due to the Covid-19 regulations. The unit of measurement is also incorrect as the adjustment target is clearly 7 and not an accumulative 21. (June 2021) | 14 | 14 | 0 | R
Strengthen Financial Sustainability and further enhance Good Governance | Develop a well-functioning communications department by updating the content of the TV screens in the reception areas at the municipal offices and submit quarterly reports to the Economic Development Portfolio Committee | Number of reports submitted to the Economic Development Portfolio Committee | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 1 | 2 |  | 0 | R | [D713] Head: Communication: The quarterly report will be submitted at the next Economic Development Portfolio Committee set to be held in August 2021. (June 2021) | 1 | 2 | 0 | R
Strengthen Financial Sustainability and further enhance Good Governance | Develop a culture of zero tolerance to corruption and dishonesty by the efficient completion of disciplinary steps in terms of the Anti-Fraud and Corruption Policy | % of transgressions initiated in terms of the Anti-Fraud and Corruption Policy | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G | [D714] Municipal Manager: None required (June 2021) | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Ensure continuous upkeep of the electronic contract register on IMIS and submit bi-annual reports to CFO on a quarterly basis after Municipal Manager has verified reports and signed it off | Number of reports submitted to the CFO after report has been verified and signed by the Municipal Manager | 0 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G | [D715] Municipal Manager: None required (June 2021) | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | % of capital budget in the Office of the Municipal Manager spent as at 30 June 2021 ((Actual amount spent on capital projects/Total amount budgeted for capital projects)x100) | % of capital budget in the Office of the Municipal Manager spent as at 30 June 2021 ((Actual amount spent on capital projects/Total amount budgeted for capital projects)x100) | 0% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 71% | R | [D716] Municipal Manager: To rectify this situation the Finance Direcorate was requested not to allocate capital projects under the co-ordination Manager of Strategic Services (co-ordinator of the Wards), but rather under the functional department that must execute the capital project. (During this year the maintenance of Municipal buildings could not be finalised). (June 2021) | 95% | 95% | 71% | R
Facilitate an enabling environment for economic growth | Ensure compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment database and submit quarterly reports to Portfolio Committee on compliance | Number of reports submitted to Portfolio Committee of compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment databasi. | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G | [D718] Municipal Manager: None required (June 2021) | 1 | 1 | 1 | G
Summary of Results: Office of the Municipal Manager
N/A | KPI Not Yet Applicable |  | 1
R | KPI Not Met |  | 3
O | KPI Almost Met |  | 2
G | KPI Met |  | 8
G2 | KPI Well Met |  | 0
B | KPI Extremely Well Met |  | 2
| Total KPIs: |  | 16
Corporate Services
Strategic Objective | KPI Name | Description of Unit of Measurement | Baseline | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Strengthen Financial Sustainability and further enhance Good Governance | The percentage of the Corporate Services capital budget excl grant funding actually spent on capital projects as at 30 June 2021 (Actual amount spent on capital projects/ Total amount budgeted for capital projects) X100 | % of Capital budget excl grant funding spent as at 30 June 2021 [(Actual amount spent on capital projects/ Total amount budgeted for capital projects) X 100] | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 99.63% | G2 |  | 95% | 95% | 99.63% | G2
Strengthen Financial Sustainability and further enhance Good Governance | Revise the organisational structure to be aligned with the "Diensstaat"-Policy BR 762 31/03/2009 and submit to Municipal Manager by 30 June 2021 | Number of organisational structure revisions to be aligned with the "Diensstaat"-policy BR 762 31/03/2009 and submitted to Municipal Manager by 30 June 2021 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Sustainable and inclusive living environment | Monitoring of the approved RSEP project plan for Bergrivier within the approved budget | No of Quarterly Technical meetings of RSEP co-ordinated and minutes submitted to the Corporate Services Portfolio Committee | 4 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop a culture of zero tolerance to corruption and dishonesty by the efficient completion of disciplinary steps in terms of the Anti-Fraud and Corruption Policy | % of transgressions initiated in terms of the Anti-Fraud and Corruption Policy | 1% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | 95% of training budget spent by 30 June 2021 to implement the Work Place Skills Plan (Total amount spent on training/Total amount budgeted)x100) | % of the training budget spent by 30 June 2021 to implement the Work Place Skills Plan | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 100% | G2 |  | 95% | 95% | 100% | G2
Strengthen Financial Sustainability and further enhance Good Governance | Develop an annual departmental strategy for Human Resources and submit to Portfolio Committee by 15 December 2020 | No of strategies submitted to Portfolio Committee by 15 December 2020 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Develop an annual departmental strategy for Planning and Development and submit to Portfolio Committee by 15 December 2020 | No of strategies submitted to Portfolio Committee by 15 December 2020 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Develop an annual departmental strategy for Administration and submit to Portfolio Committee by 15 December 2020 | No of strategies submitted to Portfolio Committee by 15 December 2020 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Effectively manage and ensure compliance on a quarterly basis of all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | % of quarterly compliance with all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Stand-Alone | 95% | 0% | 95% |  | 100% | G2 |  | 95% | 95% | 100% | G2
Strengthen Financial Sustainability and further enhance Good Governance | Evaluate the performance of all staff with performance contracts (T12 - T18) on an annual basis according to the agreed upon performance contracts before 30 June 2021 | % of performance evaluations of all staff with performance contracts (T12 - T18) according to the agreed upon performance contracts before 30 June 2021 | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Last Value | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Update the Eunomia system on a monthly basis to ensure that there is adherence to the regulatory and statutory requirements of all relevant legislation and regulations and submit to EMC on a monthly basis | % of Eunomia updates to ensure the adherence to the regulatory and statutory requirements of all relevant legislation and regulations | 12% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Ensure continuous upkeep op the electronic contract register on IMIS and submit bi-annual reports to the Municipal Manager after Director has verified reports and signed it offoff | Number of reports of contract register submitted to the Municipal Manager by 30 June 2021 after Director verified report and signed it off | 0 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop a flow chart of how complaints and enquiries must be managed into the IMIS complaint system and submit to Director's meeting by 15 December 2020 | Number of flow charts developed of how complaints and enquiries must be managed into the IMIS complaint system and submitted to Director's meeting by 15 December 2020 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Review the Service Delivery Charter and submit to EMC before 30 June 2021 | Number of reviewed Service Delivery Charters submitted to EMC before 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Conduct an internal skills audit of the whole staff complement for optimal utilizationi of required skills and submit report via Standing Committee to EMC before 31 March 2021 | Number of internal skills sudits conducted of the whole staff complement for optimal utilization of required skills submitted to EMC before 31 March 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Facilitate an enabling environment for economic growth | Ensure compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment database and submit quarterly reports to Portfolio Committee on compliance | Number of reports submitted to Portfolio Committee of compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment databasi. | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Summary of Results: Corporate Services
N/A | KPI Not Yet Applicable |  | 5
R | KPI Not Met |  | 0
O | KPI Almost Met |  | 0
G | KPI Met |  | 8
G2 | KPI Well Met |  | 3
B | KPI Extremely Well Met |  | 0
| Total KPIs: |  | 16
Community Services
Strategic Objective | KPI Name | Description of Unit of Measurement | Baseline | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Promote a safe, healthy, educated and integrated community | 95% spent of library grant by 30 June 2021 i.t.o approved business plan [(Actual amount spent/Total allocation received)x100] | % of library grant spent by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 87.97% | O | [D622] Head Library Services: The library spending are only preliminary figures and the Directorate awaits on the final spending from the finance department. (June 2021) | 95% | 95% | 87.97% | O
Promote a safe, healthy, educated and integrated community | Collect 95% of budgeted income by 30 June 2021 for speeding fines (Excl budgeted debt provision) [(Actual amount collected/total amount budgeted) x 100] | % of budgeted income for speeding fines collected by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 133.4% | G2 |  | 95% | 95% | 133.4% | G2
Strengthen Financial Sustainability and further enhance Good Governance | Collect 95% of budgeted income by 30 June 2021 for resorts (Excl budgeted debt provision)[(Actual amount collected /total amount budgeted)x100] | % of budgeted income for resorts collected by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 152.5% | B |  | 95% | 95% | 152.5% | B
Strengthen Financial Sustainability and further enhance Good Governance | Develop a culture of zero tolerance to corruption and dishonesty by the efficient completion of disciplinary steps in terms of the Anti Fraud and Corruption Policy . | % of transgressions inititated in terms of the Anti-Fraud and Corruption Policy | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Sustainable and inclusive living environment | Facilitate 80 % of title deeds transferred to eligible beneficiaries by 30 June 2021 | % of title deeds transferred to eligible beneficiaries by 30 June 2021 | 80% | 80% | 80% | Whole of Municipality: All | Percentage | Last Value | 80% | 0% | 80% |  | 98% | G2 |  | 80% | 80% | 98% | G2
Sustainable and inclusive living environment | Submit funding applications to the Provincial Department of Human Settlements for construction of top structures and/or serving of plots by 30 June 2021 | Number of submissions to obtain approval from the Provincial Department of Human Settlements for the construction of top structures and/or serving of plots by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Facilitate an enabling environment for economic growth | Monitor the performance of Bergrivier Tourism Organisation in accordance with the SLA by 30 June 2021 | Number of reports submitted from BTO to Portfolio Committee by 30 June 2021 | 4 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Promote a safe, healthy, educated and integrated community | Develop a Disaster Management Contingency Plan and submit to Portfolio Committee by 30 June 2021 | Number of Disaster Management Contingency Plans developed and submitted to Portfolio Committee by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Promote a safe, healthy, educated and integrated community | Implement a smoke alarm project in the 137 service site project in Velddrif and submit report to Community Services Portfolio Committee by 31 March 2021 | Number of reports submitted to Community Services Portfolio Committee on smoke alarm units installed in the 137 service site project in Velddrif by 31 March 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Sustainable Service Delivery | Compile festive season preparedness plan and submit to the Director Community Services for approval before 30 September 2020. | Number of festive season preparedness plans submitted to the Director Community Services for approval before 30 September 2020. | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Promote a safe, healthy, educated and integrated community | Submit to the Department of Local Government and/or the National Department of Sport and Recreation an application for sport infrastructure funding by 31 March 2021 | Number of funding applications submitted to Department of Local Government and/or the National Department of Sport and Recreation by 31 March 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Promote a safe, healthy, educated and integrated community | Review the by-law relating to prevention of public nuisances and public nuisances arising from the keeping of animals and submit to Council by 30 June 2021 | Number of by-laws reviewed relating to public nuisance and submitted to Council by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Sustainable Service Delivery | 95% of the capital budget of Directorate: Community Services spent by 30 June 2021 ((Total amount spent/Total allocation received)x100) | % of capital budget of Directorate: Community Services spent by 30 June 2021 | 0% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 92.54% | O | [D638] Head: Community Facilities: A few invoices from Capital Projects still needs to be captured and paid. This will leads that the percentage spending will increase above the required target. The finance department will on a later stage provide the final spending. (June 2021) | 95% | 95% | 92.54% | O
Strengthen Financial Sustainability and further enhance Good Governance | Effectively manage and ensure compliance on a quarterly basis of all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | % of quarterly compliance with all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Stand-Alone | 95% | 0% | 95% |  | 85.71% | O | [D634] Director Community Services: As soon as we receive the final spending from the finance department all KPI's will be met. (June 2021) | 95% | 95% | 85.71% | O
Strengthen Financial Sustainability and further enhance Good Governance | Evaluate the performance of all staff with performance contracts (T12 - T18) on an annual basis according to the agreed upon performance contracts before 30 June 2021 | % of performance evaluations of all staff with performance contracts (T12 - T18) according to the agreed upon performance contracts before 30 June 2021 | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Last Value | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Update the Eunomia system on a monthly basis to ensure that there is adherence to the regulatory and statutory requirements of all relevant legislation and regulations | Percentage of Eunomia updates to ensure the adherence to the regulatory and statutory requirements of all relevant legislation and regulations | 12% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Ensure continuous upkeep op the electronic contract register on IMIS and submit bi-annual reports to the Municipal Manager after Director has verified reports and signed it off | Number of reports of contract register submitted to the Municipal Manager by 30 June 2021 after Director verified report and signed it off | 0 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Sustainable Service Delivery | Revision of the maintenance plan in respect of all current infrastructure and submit via Community Services Portfolio Committee to EMC before 31 March 2021 | Number of maintenance plans revised in respect of all current infrastructure and submitted to via Community Services Portfolio Committee by EMC by 31 March 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Promote a safe, healthy, educated and integrated community | Develop a strategy in conjunction with national and provincial safety sectors and local stakeholders to ensure community safety and submit via the Community Services Portfolio Committee to EMC before 28 February 2021 | Number of community safety strategies developed in conjunction with national and provincial safety sector and local stakeholders submitted to EMC via Community Services Portfolio Committee before 28 February 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Facilitate an enabling environment for economic growth | Ensure compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment database and submit quarterly reports to Portfolio Committee on compliance | Number of reports submitted to Portfolio Committee of compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment databasi. | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Summary of Results: Community Services
N/A | KPI Not Yet Applicable |  | 5
R | KPI Not Met |  | 0
O | KPI Almost Met |  | 3
G | KPI Met |  | 9
G2 | KPI Well Met |  | 2
B | KPI Extremely Well Met |  | 1
| Total KPIs: |  | 20
Council
Strategic Objective | KPI Name | Description of Unit of Measurement | Baseline | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Strengthen Financial Sustainability and further enhance Good Governance | Number of formal households that receive piped water (credit & pre-paid water) that is connected to the municipal water infrastructure network as at 30 June 2021 | Number of households which are billed for water or have prepaid meters as at 30 June 2021 | 9 | 9218 | 9218 | Whole of Municipality: All | Number | Last Value | 9218 | 0 | 9218 |  | 9533 | G2 |  | 9218 | 9218 | 9533 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Number of formal households connected to the municipal electrical infrastructure network (credit & prepaid electrical metering) (Excl Eskom areas) at 30 June 2021 | Number of households billed for electricity or have prepaid meters (Excl Eskom areas) at 30 June 2021 ( CONTOUR + Active meters) | 10 | 10201 | 10201 | Whole of Municipality: All | Number | Last Value | 10201 | 0 | 10201 |  | 9393 | O | [D644] Manager: Income: The actual is less due to an system cleanup of old meters not correctly removed, as per COMAF during 19/20 Audit (June 2021) | 10201 | 10201 | 9393 | O
Strengthen Financial Sustainability and further enhance Good Governance | Number of formal households connected to the municipal waste water sanitation/sewerage network for sewerage service, irrespective of number of water closets (toilets) at 30 June 2021 | Number of households which are billed for sewerage at 30 June 2021 | 7 | 7508 | 7508 | Whole of Municipality: All | Number | Last Value | 7508 | 0 | 7508 |  | 7526 | G2 |  | 7508 | 7508 | 7526 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Number of formal households for which refuse is removed once per week at 30 June 2021 | Number of households which are billed for refuse removal at 30 June 2021 | 9 | 9600 | 9600 | Whole of Municipality: All | Number | Last Value | 9600 | 0 | 9600 |  | 9625 | G2 |  | 9600 | 9600 | 9625 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Provide free basic water to indigent households | Number of households receiving free basic water | 1 | 1950 | 1950 | Whole of Municipality: All | Number | Stand-Alone | 1950 | 0 | 1950 |  | 2128 | G2 | [D647] Manager: Income: Indigent applications increased due to Covid lockdown. (June 2021) | 1950 | 1950 | 2128 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Provide free basic electricity to indigent households | Number of households receiving free basic electricity | 800 | 1550 | 1550 | Whole of Municipality: All | Number | Stand-Alone | 1550 | 0 | 1550 |  | 1899 | G2 | [D648] Manager: Income: Indigent applications increased due to Covid lockdown. (June 2021) | 1550 | 1550 | 1899 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Provide free basic sanitation to indigent households | Number of households receiving free basic sanitation | 1 | 1650 | 1650 | Whole of Municipality: All | Number | Stand-Alone | 1650 | 0 | 1650 |  | 1886 | G2 | [D649] Manager: Income: Indigent applications increased due to Covid lockdown. (June 2021) | 1650 | 1650 | 1886 | G2
Strengthen Financial Sustainability and further enhance Good Governance | Provide free basic refuse removal to indigent households | Number of households receiving free basic refuse removal | 1800 | 1950 | 1950 | Whole of Municipality: All | Number | Stand-Alone | 1950 | 0 | 1950 |  | 2128 | G2 | [D650] Manager: Income: Indigent applications increased due to Covid lockdown. (June 2021) | 1950 | 1950 | 2128 | G2
Strengthen Financial Sustainability and further enhance Good Governance | The percentage of a municipality's personnel and training budget actually spent on implementing its workplace skills plan as at 30 June 2021 [(Total expenditure on training/total personnel budget)/100] | % of personnel and training budget spent on training [(Total expenditure on training/ total personnel budget) /100] as at 30 June 2021 | 1% | 1% | 1% | Whole of Municipality: All | Percentage | Last Value | 1% | 0% | 1% |  | 0.07% | R | [D651] Director Corporate Services: Council must make appropriate provision within the next year financial year. (June 2021) | 1% | 1% | 0.07% | R
Strengthen Financial Sustainability and further enhance Good Governance | Financial viability measured into municipality's ability to meet its service debt obligations as at 30 June 2021 (Short Term Borrowing + Bank Overdraft + Short Term Lease + Long Term Borrowing + Long Term Lease) / Total Operating Revenue - Operating | Debt to Revenue as at 30 June 2021 (Short Term Borrowing + Bank Overdraft + Short Term Lease + Long Term Borrowing + Long Term Lease) / Total Operating Revenue - Operating Conditional Grant) | 20% | 24% | 24% | Whole of Municipality: All | Percentage | Reverse Last Value | 24% | 0% | 24% |  | 18.63% | B | [D652] Manager: Budget and Treasury Office: Should be meassured in the negative value. (June 2021) | 24% | 24% | 18.63% | B
Strengthen Financial Sustainability and further enhance Good Governance | Financial viability measured in terms of outstanding service debtors as at 30 June 2021 (Total outstanding service debtors/ revenue received for services) | Service debtors to revenue as at 30 June 2021 (Total outstanding service debtors/ revenue received for services) | 34% | 45% | 45% | Whole of Municipality: All | Percentage | Reverse Last Value | 45% | 0% | 45% |  | 22.4% | B |  | 45% | 45% | 22.4% | B
Strengthen Financial Sustainability and further enhance Good Governance | Financial viability measured in terms of available cash to cover fixed operating expenditure as at 30 June 2021 ((Cash and Cash Equivalents Unspent Conditional Grants Overdraft) + Short Term Investment ) /Monthly Fixed Operational Expenditure exc (Dep | Cost coverage as at 30 June 2021 ((Cash and Cash Equivalents - Unspent Conditional Grants Overdraft) + Short Term Investment) / Monthly Fixed Operational Expenditure excl (Depreciation, Amortisation, and Provision for Bad Debts, Impairment and Loss on Disposal of Assets)) | 2.9 | 2.25 | 2.25 | Whole of Municipality: All | Number | Last Value | 2.25 | 0 | 2.25 |  | 4.98 | B |  | 2.25 | 2.25 | 4.98 | B
Summary of Results: Council
N/A | KPI Not Yet Applicable |  | 0
R | KPI Not Met |  | 1
O | KPI Almost Met |  | 1
G | KPI Met |  | 0
G2 | KPI Well Met |  | 7
B | KPI Extremely Well Met |  | 3
| Total KPIs: |  | 12
Financial Services
Strategic Objective | KPI Name | Description of Unit of Measurement | Baseline | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Strengthen Financial Sustainability and further enhance Good Governance | Improve the net debt collection period by 30 June 2021 | Number of outstanding debtor days by 30 June 2021 | 0 | 120 | 120 | Whole of Municipality: All | Number | Reverse Last Value | 120 | 0 | 120 |  | 75.4 | B | [D265] Accountant: Credit Control: If the actual is less than the target, it should not be red. The performance is then better. (June 2021) | 120 | 120 | 75.4 | B
Strengthen Financial Sustainability and further enhance Good Governance | Monitor veriments in the operational budget in accordance with the MFMA to enable efficient and effective service delivery and submit reports to the Finance Portfolio Committee on a quarterly basis | Number of reports submitted to the Finance Portfolio Committee to monitor veriments in the operational budget in accordance with the MFMA to enable efficient and effective service delivery | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Conduct 1 series workshops to business on compliance with municipal SCM regulation requirements to promote business opportunities in Bergriver Municipal Area through the municipal budget by 30 June 2021 | Number of workshops conducted to businesses on compliance with SCM regulation requirements by 30 June 2021 | 1 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Update the Eunomia system on a monthly basis to ensure that there is adherence to the regulatory and statutory requirements of all relevant financial legislation and regulations | Percentage of Eunomia updates to ensure the adherence to the regulatory and statutory requirements of all relevant financial legislation and regulations | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Implement a customary query dedicated email functionality to improve customer care and client enquiries in the Directorate Financial Services and submit a report to the Financial Portfolio Committee by September 2020 | Number of reports on the enhanced utilisation of the municipal customer care dedicated e-mail address system submitted to the Financial Portfolio Committee by September 2020 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Submit a report for the writing off of unrecoverable debt to the Financial Portfolio Committee by December 2020 and June 2021 | Number of reports submitted for the writing off of unrecoverable debt to the Financial Portfolio Committee by December 2020 and June 2021 | 1 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Achieve a payment percentage of 96% as at 30 June 2021 ((Gross Debtors Closing Balance + Billed Revenue - Gross Debtors Opening Balance + Bad Debts Written Off)/Billed Revenue) x 100) | Payment % as at 30 June 2021 ((Gross Debtors Closing Balance + Billed Revenue - Gross Debtors Opening Balance + Bad Debts Written Off) /Billed Revenue) x 100) | 96% | 92% | 92% | Whole of Municipality: All | Percentage | Last Value | 92% | 0% | 92% |  | 96.6% | G2 |  | 92% | 92% | 96.6% | G2
Strengthen Financial Sustainability and further enhance Good Governance | Develop a culture of zero tolerance to corruption and dishonesty by the efficient completion of disciplinary steps in terms of the Anti Fraud and Corruption Policy . | % of identified transgressions inititated in terms of the Anti-Fraud and Corruption Policy | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Effectively manage and ensure compliance on a quarterly basis of all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | % of quarterly compliance with all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Stand-Alone | 95% | 0% | 95% |  | 95% | G |  | 95% | 95% | 95% | G
Strengthen Financial Sustainability and further enhance Good Governance | Evaluate the performance of all staff with performance contracts (T12 - T18) on an annual basis according to the agreed upon performance contractst before 30 June 2021 | % of performance evaluations of all staff with performance contracts (T12 - T18) according to the agreed upon performance contracts before 30 June 2021 | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Last Value | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Ensure continuous upkeep op the electronic contract register on IMIS and submit bi-annual reports to the Municipal Manager after Director has verified reports and signed it offoff | Number of reports of contract register submitted to the Municipal Manager by 30 June 2021 after Director verified report and signed it off | 0 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop 3 separate cost reflective tariffs model for water, sewer and refuse charges and submit to Finance Portfolio Committee by 31 March 2021 | Number of cost reflective tariff models developed and submitted to Finance Portfolio Committee by 31 March 2021 | 0 | 1.5 | 3 | Whole of Municipality: All | Number | Stand-Alone | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Strengthen Financial Sustainability and further enhance Good Governance | Implement the Approved Revenue Enhancement strategy to improve revenue generation and collection and submit quarterly reports to the Finance Portfolio Committee | Number of reports submitted to Finance Portfolio Committee on the implementation of the approved Revenue Enhancement Strategy | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop a costing model for maintenance to reflect true cost of maintenance and submit report to Finance Portfolio Committee by 30 June 2021 | Number of reports submitted to Finance Portfolio Committee before 30 June 2021 on a costing model for maintenance | 0 | 1 | 1 | Whole of Municipality: All | Number | Stand-Alone | 0 | 1 | 1 |  | 1 | G |  | 0 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Launch an awareness campaign before 30 September 2020 to encourage municipal account holders to receive their municipal account electronically and submit a report to the Finance Portfolio Committee | Number of reports submitted to the Portfolio Committeemon an awareness campaign launched before 30 September 2020 to encourage municipal account holders to receive their municipal account electronically | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 0 | N/A |  | 0 | 0 | 0 | N/A
Facilitate an enabling environment for economic growth | Ensure compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment database and submit quarterly reports to Portfolio Committee on compliance | Number of reports submitted to Portfolio Committee of compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment databasi. | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Summary of Results: Financial Services
N/A | KPI Not Yet Applicable |  | 3
R | KPI Not Met |  | 0
O | KPI Almost Met |  | 0
G | KPI Met |  | 11
G2 | KPI Well Met |  | 1
B | KPI Extremely Well Met |  | 1
| Total KPIs: |  | 16
Technical Services
Strategic Objective | KPI Name | Description of Unit of Measurement | Baseline | Original Annual Target | Revised Annual Target | MSC | Target Type | Calculation Type | Quarter ending June 2021 | [6 empty] | Overall Performance for Quarter ending June 2021 to Quarter ending June 2021
[9 empty] | Original Target | Adjustment | Target | Target Description | Actual | R | Departmental KPI: Corrective Measures | Original Target | Target | Actual | R
Sustainable Service Delivery | Limit unaccounted for water to 10% by 30 June 2021 {(Number of Kilolitres Water Purchased or Purified minus Number of Kilolitres Water Sold (incl free basic water) / Number of Kilolitres Water Purchased or Purified × 100} | % unaccounted water by 30 June 2021 {(Number of Kilolitres Water Purchased or Purified minus Number of Kilolitres Water Sold (including Free basic water ) / Number of Kilolitres Water Purchased or Purified × 100} | 10% | 10% | 10% | Whole of Municipality: All | Percentage | Reverse Last Value | 10% | 0% | 10% |  | 15.96% | R | [D503] Director: Technical Services: Finance Department must give permission that Technical Department can purchase additional bulk meter and keep in Departmental stores to prevent water losses at big consumers. Technical Department will continue with the replacement of all old water meters with SMART metering. (June 2021) | 10% | 10% | 15.96% | R
Sustainable Service Delivery | Limit unaccounted for electricity to 10% by 30 June 2021 {(Number of Electricity Units Purchased and/or Generated - Number of Electricity Units Sold (incl Free basic electricity)) / Number of Electricity Units Purchased and/or Generated) × 100} | % unaccounted electricity by 30 June 2021 {(Number of Electricity Units Purchased and/or Generated - Number of Electricity Units Sold (incl. Free basic electricity) )/ Number of Electricity Units Purchased and/or Generated) × 100} | 10% | 10% | 10% | Whole of Municipality: All | Percentage | Reverse Last Value | 10% | 0% | 10% |  | 12.14% | R | [D504] Director: Technical Services: Continue with the close monitoring of the bulk users. (June 2021) | 10% | 10% | 12.14% | R
Sustainable Service Delivery | 95% of MIG conditional grant spent by 30 June 2021 to upgrade infrastructure [(Total amount spent/ Total amount allocated)x100] | % of MIG conditional grant spent by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 71.5% | O | [D505] Director: Technical Services: We applied for roll over of funds not to lose the funding. This has been supported by DCoG. 4 new projects were eventually approved after we had meetings with DCoG national. Spending will be on track in 2021/22 (June 2021) | 95% | 95% | 71.5% | O
Sustainable Service Delivery | 95% of conditional road maintenance operational grant spent by 30 June 2021 [(Total amount spent/ Total allocation received)x100] as budgeted in the Bergrivier Municipality Operational Budget | % of conditional road maintenance operational grant spent by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 100% | G2 |  | 95% | 95% | 100% | G2
Sustainable Service Delivery | 95% of the capital budget of Directorate: Technical Services spent by 30 June 2021 ((Total amount spent/Total allocation received)x100) | % of capital budget of Directorate: Technical Services spent by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 96% | G2 |  | 95% | 95% | 96% | G2
Sustainable Service Delivery | Compile a draft Infrastructure Growth Plan, inclusive of a Water Augmentation Plan, and submit by 30 June 2021 to Executive Mayoral Committee | Number of Draft Infrastructure Growth Plans, inclusive of a Water Augmentation Plan, submitted to Executive Mayoral Committee by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Sustainable Service Delivery | Develop a policy for future Small Scale Embedded Electricity Generation (SSEMG) and submit by 30 June 2021 to Executive Mayoral Committee | Number of policies for future Small Scale Embedded Electricity Generation submitted to Executive Mayoral Committee by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 0 | R | [D509] Director: Technical Services: Policy will be approved by Council end of July 2021 (June 2021) | 1 | 1 | 0 | R
Sustainable Service Delivery | Revise the Integrated Waste Management by-law and submit to Executive Mayoral Committee by 30 June 2021 | Number of Integrated Waste Management by-laws revised and submitted to Executive Mayoral Committee by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Sustainable Service Delivery | Raise public awareness on recycling to reduce household waste with awareness initiatives | Number of awareness initiatives | 2 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 2 | B |  | 1 | 1 | 2 | B
Sustainable Service Delivery | 95% spend of transferred funds before September 2020 (Jan 2019 - Dec 2020) for the implementation of the approved business plan on the waste programme by 30 June 2021 ((Total amount spent/Total approved budget) x 100) (subject to international funding | % of funds transferred before September 2020 (Jan 2019 - Dec 2020) spend by 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 98.87% | G2 |  | 95% | 95% | 98.87% | G2
Sustainable Service Delivery | 95% water quality level obtained as per SANS 241 physical & micro parameters as at 31 December 2020 and 30 June 2021 | % water quality level as at 31 December 2020 and 30 June 2021 | 95% | 95% | 95% | Whole of Municipality: All | Percentage | Last Value | 95% | 0% | 95% |  | 99.1% | G2 |  | 95% | 95% | 99.1% | G2
Sustainable Service Delivery | Sign SLA's for each development to facilitate an environment conducive to infrastructure development in partnership with the developer and/or investors. Signed SLA's/total number of developments where SLA's are required) | % of developments with Signed SLA's with developers and/or investors | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Sustainable Service Delivery | Undertake quarterly inspections per major town for building transgressions and submit report to Portfolio Committee with findings and law enforcement actions instituted | Number of reports submitted to the Portfolio Committee | 2 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Facilitate an enabling environment for economic growth | Create full time equivalents (FTE's) in terms of the EPWP programme by 30 June 2021 | Number of FTE's created by 30 June 2021 | 61 | 65 | 65 | Whole of Municipality: All | Number | Carry Over | 65 | 0 | 65 |  | 105 | B |  | 65 | 65 | 105 | B
Strengthen Financial Sustainability and further enhance Good Governance | 100% of all complaints registered on IMIS are being attended to within one (1) week after complaint was lodged | % of complaints registered on IMIS being attended to within one week after complaint was lodged | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Ensure continuous upkeep op the electronic contract register on IMIS and submit bi-annual reports to the Municipal Manager after Director has verified reports and signed it offoff | Number of reports of contract register submitted to the Municipal Manager by 30 June 2021 after Director verified report and signed it off | 0 | 2 | 2 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Revision of the technical functions in the Blackout Plan and submit to Technical Portfolio Committee by 30 June 2021 | Number of revisions of the technical functions in the Blackout Plan and submit to Technical Portfolio Committee by 30 June 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Strengthen Financial Sustainability and further enhance Good Governance | Revision of the maintenance plan in respect of all current infrastructure and submit via Technical Portfolio Committee to EMC before 28 February 2021 | Number of maintenance plans revised in respect of all current infrastructure and submitted to Technical Services via Portfolio Committee by 28 February 2021 | 0 | 1 | 1 | Whole of Municipality: All | Number | Carry Over | 0 | 0 | 0 |  | 1 | B | [D520] Director: Technical Services: Maintenance plans didn't serve on EMC in February only at the Technical Portfolio Committee (June 2021) | 0 | 0 | 1 | B
Strengthen Financial Sustainability and further enhance Good Governance | Evaluate the performance of all staff with performance contracts (T12 - T18) on an annual basis according to the agreed upon performance contracts before 30 June 2021 | % of performance evaluations of all staff with performance contracts (T12 - T18) according to the agreed upon performance contracts before 30 June 2021 | 0% | 100% | 100% | Whole of Municipality: All | Percentage | Last Value | 100% | 0% | 100% |  | 0% | R |  | 100% | 100% | 0% | R
Strengthen Financial Sustainability and further enhance Good Governance | Effectively manage and ensure compliance on a quarterly basis of all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | % of quarterly compliance with all TL SDBIP KPI's in respect of accountable levels of management in accordance with the performance management policy | 0% | 95% | 95% | Whole of Municipality: All | Percentage | Stand-Alone | 95% | 0% | 95% |  | 0% | R |  | 95% | 95% | 0% | R
Strengthen Financial Sustainability and further enhance Good Governance | Update the Eunomia system on a monthly basis to ensure that there is adherence to the regulatory and statutory requirements of all relevant legislation and regulations and submit to EMC on a monthly basis | % of Eunomia updates to ensure the adherence to the regulatory and statutory requirements of all relevant legislation and regulations | 12% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Strengthen Financial Sustainability and further enhance Good Governance | Develop a culture of zero tolerance to corruption and dishonesty by the efficient completion of disciplinary steps in terms of the Anti-Fraud and Corruption Policy | % of transgressions initiated in terms of the Anti-Fraud and Corruption Policy | 100% | 100% | 100% | Whole of Municipality: All | Percentage | Stand-Alone | 100% | 0% | 100% |  | 100% | G |  | 100% | 100% | 100% | G
Facilitate an enabling environment for economic growth | Ensure compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment database and submit quarterly reports to Portfolio Committee on compliance | Number of reports submitted to Portfolio Committee of compliance with the SOP developed providing preference to temporary employees from indigent households registered on the unemployment databasi. | 0 | 4 | 4 | Whole of Municipality: All | Number | Accumulative | 1 | 0 | 1 |  | 1 | G |  | 1 | 1 | 1 | G
Summary of Results: Technical Services
N/A | KPI Not Yet Applicable |  | 0
R | KPI Not Met |  | 5
O | KPI Almost Met |  | 1
G | KPI Met |  | 10
G2 | KPI Well Met |  | 4
B | KPI Extremely Well Met |  | 3
| Total KPIs: |  | 23
Overall Summary of Results
N/A | KPI Not Yet Applicable |  | 14
R | KPI Not Met |  | 9
O | KPI Almost Met |  | 7
G | KPI Met |  | 46
G2 | KPI Well Met |  | 17
B | KPI Extremely Well Met |  | 10
| Total KPIs: |  | 103
Report generated on 23 July 2021 at 07:44.